|  |
| --- |
| **PM-02-PS03:Develop a Work Breakdown Structure** |

Topic elements to be covered include:

1. Develop a Work Breakdown Structure

**Resources:**

|  |  |
| --- | --- |
| **Knowledge** | **Information from Project Manager Curriculum**  |
| National Curriculum Framework | 121905000-KM-01, Introductory studies for Project Managers,KM-01-KT03: Project management processesKT0302 Planning |

Use the following WBS Completion Checklist to ensure that everything is included in your table: **WBS Completion Checklist**

|  |  |
| --- | --- |
| **Appropriate level of detail**: Continue to break the work down until a task list is developed which meets the following criteria: | **✓ / 🗴** |
| One (and only one) owner can be assigned to each of the lowest level tasks |  |
| Clearly defined outputs are evident for each task |  |
| Quality can be monitored through performance criteria associated with each output |  |
| The tasks communicate the work to be accomplished to the person who is accountable |  |
| The likelihood that a task is omitted or workflow forgotten is minimized |  |
| Each task is well enough defined and small enough so that estimates of duration are credible |  |
| The project is broken down to the level at which you want to track |  |
| As a general rule, the lowest level tasks should have durations between two and twenty days and effort that equates to not more than 1 person week |  |
| **No forgotten tasks:** Project delays are often caused by forgotten tasks, rather than inaccurate estimates. Ensure you have included tasks for: | **✓ / 🗴** |
| Planning the project |  |
| Approval cycles |  |
| Key project meetings |  |
| Management/customer interfaces |  |
| Quality inspections/fixing defects |  |
| Training |  |
| Management |  |
| Test planning, development and execution |  |
| Project reviews and project closing |  |
| **Signature** |  | **Date** |  |